## Now → In Progress
Task ID | Task Name | Assignee | Phase | Lane | Pod | Due Date | Status | Priority | Description | Evidence
P0-NAVI-UNZIP | Unzip onboarding kit and push to staging | Navi | Phase 0 — Kickoff & Intake | Audit | App & Product Delivery | 2025-10-05 | In Progress | High | Extract GG_Launch_Onboarding_kit_2025-10-05.zip to repo root; verify structure; push to 'staging' branch. | git log -1, pricing screenshot, ls outputs
P0-OS-VERIFY | Verify structure & PricingTable renders | OS | Phase 0 — Kickoff & Intake | Audit | OS | 2025-10-05 | In Progress | High | Confirm /docs, /src/components, /src/lib, /config/flags, /public; run pricing page; flip flags. | screenshots, console flag test
P1-SENT-SEC001 | Cookies+CSRF+Helmet+HSTS+CORS minimal | Sentinel | Phase 1 — Security & Data Integrity | Hardening | App & Product Delivery | 2025-10-05 | In Progress | Highest | Set HttpOnly/Secure/SameSite cookies; CSRF on mutating routes; Helmet CSP+HSTS; restrict CORS. | curl -I, securityheaders screenshot
P1-FORGE-DB001 | Idempotent Time→Invoice import (txn + dup guard) | Forge | Phase 1 — Security & Data Integrity | Hardening | App & Product Delivery | 2025-10-05 | In Progress | Highest | Reject already-linked timelogs; wrap in transaction; rollback on error. | DB before/after, API response
P1-FILE-002 | Filing Cabinet soft-delete + 7d restore + audit | Forge | Phase 1 — Security & Data Integrity | Hardening | App & Product Delivery | 2025-10-05 | In Progress | High | Implement soft-delete, 7-day restore, and audit trail for bulk operations. | UI GIF, audit log export
P1-OPS-001 | One-click Export/Restore runbook | Navi | Phase 1 — Security & Data Integrity | Hardening | App & Product Delivery | 2025-10-05 | In Progress | High | Account CSV/ZIP export; restore script and validation. | ZIP export, restore log
P4-AMANI-RECRUIT | Recruit 10 founders + schedule sessions | Amani | Phase 4 — Founder Usability Circuit | Beta | App & Product Delivery | 2025-10-05 | In Progress | High | 4 freelancers, 3 sole proprietors, 3 SMB owners; schedule recordings. | calendar invites, participant list
P4-AMANI-RUN | Run 5-task script + capture SUS | Amani | Phase 4 — Founder Usability Circuit | Beta | App & Product Delivery | 2025-10-05 | In Progress | High | Tasks: project+3 tasks; time→invoice; pay link; files bulk ops; automation rule. | recordings, SUS sheet, top 5 issues
P2-PRICING | Finalize pricing page + copy | Prism | Phase 2 — Core UX & Billing | Hardening | Marketing | 2025-10-05 | In Progress | Medium | Apply copy from docs/copy_pricing.md; confirm flags & tiers render correctly. | page screenshot
P2-UTM | UTM plan applied to outbound emails + CTA links | Echo | Phase 2 — Core UX & Billing | Hardening | Marketing | 2025-10-05 | In Progress | Medium | UTM format ?utm_source={channel}&utm_medium={medium}&utm_campaign={campaign}; campaigns: launch_q4_2025, beta_invite, pricing_upgrade. | email preview, GA view
P6-DOCS | Quick Start, Pricing, ToS ready | Storybloom | Phase 6 — Launch Prep & GA | Launch | Marketing/Docs | 2025-10-05 | In Progress | Medium | Author and finalize docs for launch readiness. | published docs links
P2-MARGINS | Margin model per tier + fee policy | Ledger | Phase 2 — Core UX & Billing | Hardening | Finance | 2025-10-05 | In Progress | High | Confirm Core/Plus/Pro pricing; outline upgrade drivers; decide Stripe fee handling. | one-pager model
P2-DRIVERS | Upgrade drivers validation | Stratēga | Phase 2 — Core UX & Billing | Hardening | Strategy | 2025-10-05 | In Progress | Medium | Validate which features push upgrades (AI Proposals, Client Portal, Analytics, Automation Power). | competitive notes